# 6-Axis Robot Arm Pick-and-Place with Depth Camera
Executable Project Plan & Timeline

## Project Assumptions

- Time availability: ~2 hours/day, ~10–12 hours/week
- Robot: 6-axis arm driven by stepper motors (existing low-level motor control code available)
- Goal: Automatically detect misplaced toys using a depth camera and return them to correct positions
- Software stack: ROS2 + MoveIt + Simulation (Isaac Sim or Gazebo)
- Plan is iterative and expected to evolve

## Phase 0 – Architecture & Scope Definition (Week 0, 3–5 days)

Objectives:
- Decide ROS2 distribution and simulator
- Define system architecture and success criteria

Deliverables:
- Architecture diagram (ROS nodes and data flow)
- Repository structure created
- Clear success definition (toy moved back within tolerance)

Notes:
- Perception and simulator choice may change later

## Phase 1 – Robot Modeling & MoveIt Setup (Weeks 1–2)

Week 1:
- Create URDF/Xacro model of robot
- Define joints, limits, frames, and TCP

Week 2:
- Configure MoveIt 2
- Validate planning and execution in RViz

Deliverables:
- robot_description package
- moveit_config package
- Successful pose planning and execution in simulation

## Phase 2 – Simulation World, Toys & Slots (Week 3)

Objectives:
- Create tabletop environment
- Add toy objects and slot frames
- Define correct toy-slot mappings

Deliverables:
- World spawn scripts
- Slot frames published via TF
- YAML/JSON slot definition file

## Phase 3 – Pick & Place Without Vision (Week 4)

Objectives:
- Implement full pick-and-place pipeline using ground-truth object poses

Deliverables:
- Reliable pick-and-place execution in simulation
- Retry logic for motion failures

Exit Criteria:
- ≥70% success rate using known object poses

## Phase 4 – Depth Camera Integration in Simulation (Weeks 5–6)

Week 5:
- Integrate simulated depth camera
- Validate camera TF and topics

Week 6:
- Implement basic perception (depth centroid or pose estimation)

Deliverables:
- Perception node publishing toy poses
- Robot picking toys using camera-derived poses

## Phase 5 – Task Planner & Robustness (Week 7)

Objectives:
- Build task-level state machine (detect → pick → place → verify)
- Handle failures and retries

Deliverables:
- Task planner ROS node
- Autonomous multi-cycle operation in simulation

## Phase 6 – Perception Training (Optional) (Weeks 8–9)

Track A (Recommended):
- Train object detector using synthetic data
- Depth-based pose estimation

Track B (Advanced):
- Train 6D pose estimation model

Deliverables:
- Improved perception robustness
- Performance under randomized lighting and noise

## Phase 7 – Real Hardware Integration (Weeks 10–12)

Week 10:
- Wrap stepper motor control into ROS2 interface

Week 11:
- Camera extrinsic and TCP calibration

Week 12:
- Full real-world demo: detect → pick → place → verify

Deliverables:
- Working real robot controlled via ROS2
- Demonstration video or validation record

## Phase 8 – Extensions & Refinement (Ongoing)

- Add more toy types
- Improve grasp robustness
- Introduce learning-based correction
- Optimize speed and reliability